## Index (hidden)
TSPe Support Tool Index of Forms and Charts
FORMS | Description | CHARTS | Description
Launch Meeting/Planning Forms |  | Earned Value | Planned vs. earned value and projected earned value
Use these forms to plan a new project or build |  | Plan vs. Actual Hours | Planned vs. actual hours
Project | Project startup and summary form | Defect Removal Profile | Defects removed by phase for each component
Team | Team member summary | Quality Profile
Roles | TSPe role assignments | Percent Defect Free | Percent of components that are defect free by phase
Goals | Team goals
Components | Product component list
Task | Task plan template
Schedule | Schedule plan template
QUAL-Plan | Quality plan for system and components
COMPR-Plan | Resource plan for system and components
COMPD-Plan | Defect injection/removal plan for system and components
Risks | Team risk assessment
Weekly Meeting/Tracking Forms
Use these forms for gathering data and tracking a project or build
TimeLog | Time recording Log
DefectLog | Defect recording log
Week | Weekly meeting status report
Task | Task plan template
Schedule | Schedule plan template
QUAL-Actual | Quality actuals for system and components
COMPR-Actual | Resource actuals for system and components
COMPD-Actual | Defects injected/removed for system and components
Standards
Phases | TSPe process phase standard
DefectTypes | Defect type standard
Copyright 1998 James W. Over

## Instructions
TSPi Support Tool Instructions
Strategy Development and Planning
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
Before STRAT1 | Team Leader | Fill out the project information on the Project worksheet (Name, Team name, Project name, Start Date, Instructor, Cycle). | Project!Name
Before STRAT1 | Team Leader | Enter the team member names, initials, phone numbers, e-mail addresses, and filenames for the team members workbooks in the Team worksheet. | Team!B2
Before STRAT1 | Team Leader | Enter the role assignments on the Roles worksheet. | Roles!B2
STRAT: Establish Team Goals | Planning Manager | Enter the team goals on the Goals worksheet | Goals!B3
STRAT1: Produce the Size Estimate | Planning Manager | Enter on the SUMS worksheet, the names and size estimates of all assemblies and parts for this cycle. | SUMS!B8
PLAN1: Produce the Task Plan | Planning Manager | Click the Generate Task List button to create a default task list. | Task!A8
PLAN1: Produce the Task Plan | Planning Manager | Revise the task list adding or deleting tasks as necessary. Then for each task, estimate the size where appropriate, the time, and the time for each engineer assigned to the task. | Task!A8
PLAN1: Produce the Schedule Plan | Planning Manager | Enter hours per week in the Schedule template. Hours per week are based on the total hours for the team for each week in the schedule. | Schedule!C8
| Planning Manager | Click the Update Task and Schedule Plan button on the Task Worksheet to generate a schedule. | Task!A8
PLAN1: Quality Plan | Team | Before creating the quality plan, review the quality standard in the textbook.
PLAN1: Quality Plan | Quality/Process Manager | Enter the planned defect injection rates for each phase on the SUMQ worksheet. | SUMQ!D82
PLAN1: Quality Plan | Quality/Process Manager | Enter estimated phase yields for each phase. | SUMQ!D55
PLAN1: Quality Plan | Team | Review the calculated defect removal rates and defect densities (Defects/KLOC) against the Quality Standard. If necessary, adjust planned time (Task worksheet), defect injection rates (SUMQ), or defect removal yields (SUMQ).
PLAN: Balance Workload | Planning Manager | Make 1 copy of the team workbook for each engineer. Use the filename entered on the Team worksheet (Workbook Filename). Click the Make copies... button to create the copies automatically. | Team!B2
PLAN: Balance Workload | Each engineer | Revise the tasks in the Task worksheet to reflect the individual engineers workload (e.g. delete task not assigned to you, and where you share an assignment with other engineers, set their planned hours to zero). | Task!A8
PLAN: Balance Workload | Each engineer | Revise the schedule plan on the Schedule worksheet to reflect your available hours per week. | Schedule!C8
PLAN: Balance Workload | Planning Manager | Load the engineers' individual worksheets and the consolidated team plan workbook into the same folder. Open the consolidated team plan workbook. Click the consolidate plan button on the Team worksheet to build a consolidated plan | Team!B2
PLAN: Balance Workload | All team members | If necessary, reassign tasks to balance the workload and repeat the previous 3 steps until a balanced plan is achieved. If planned times for any task change, review the quality plan and revise it if necessary.
Weekly Tracking
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
STRAT, PLAN, REQ, DES, IMP, TEST, PM | All team members | During all TSPi phases, use the time log to record data on each task. Include the assembly and phase for each task, the date, start time, interrupt time, stop time, and comments. | LOGT!A7
REQ, DES, IMP, TEST | All team members | During TSPi phases REQ, DES, IMP, and TEST, use the defect log to record data on each defect. Include the date, number, type, assembly, phase injected, phase removed, fix time, fix reference, and description | LOGD!A7
Weekly | All team members | Click the Update Project button on the Project worksheet to update individual plans. Print the Task and Schedule worksheets. | Project!Name
Weekly | All team members | Print the Task worksheet. | Task!A8
Weekly | All team members | Print the Schedule worksheet. | Schedule!A8
Weekly | All team members | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | All team members | Send a copy of your workbook to the planning manager for use in preparing the team's consolidated weekly report.
Weekly | Planning Manager | Update consolidated team plan with the current week's data and prepare status reports for the weekly meeting.
Weekly | Planning Manager | Load the individual engineers workbooks and the consolidated team workbook into the same folder. Open the consolidated team workbook. Click the Consolidate Plans button on Team worksheet to update consolidated team plan with the current week's data. | Team!F1
Weekly | Planning Manager | Select the Project worksheet and click the update project button before printing status reports for the weekly meeting. | Project!Name
Weekly | Planning Manager | Print the Task worksheet. | Task!A8
Weekly | Planning Manager | Print the Schedule worksheet. | Schedule!A8
Weekly | Planning Manager | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Earned Value -Plan vs. Actual Hours | Project!Name
Weekly during implementation and testing phases | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Defect Removal Profile -Quality Profile -Percent Defect Free | Project!Name
Project and Cycle Postmortem
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
PM | All team members | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | All team members | Select the Project worksheet and click the export button to save a copy of your data for the cycle. | Project!Name
PM | Planning Manager | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | Planning Manager | Select the SUMP worksheet and print a SUMP form for the SYSTEM and each assembly | SUMP!B2
PM | Planning Manager | Select the SUMQ worksheet and print a SUMQ form for the SYSTEM and each assembly | SUMQ!B2
PM | Planning Manager | Select the SUMS worksheet and print a SUMS form | SUMS!B8
PM | Planning Manager | Select the Project worksheet and click the export button to save a copy of the consolidated team data for the cycle. | Project!Name

## Project
TSPi | - Project Summary |  |  | Design/Code Time | 1
|  |  |  | Code Review Time | 1
Name | Lohtu | Date | 2026-07-28 13:39 | Compile Defects/KLOC | 1
Project | Lohtu-projekti | Start Date | 2003-03-03 | Unit Test Ddefects/KLOC | 1
Team | B | Instructor | Inkeri Verkamo | Design Review Time | 1
Part/Level |  | Cycle | 2 | CR | 10.4167
|  | Today's Date Override |  | COMPILE | 3.4722
Version: | TSPi.19990907. Copyright 1999 Addison Wesley . |  |  | CODEINSP | 2.7778
|  |  |  | UT | 2.0833
|  |  |  | IT | 0
|  |  |  | ST | 0
|  |  |  | 1 Year | 0
|  |  |  | Product Life | 0
Draw Chart
Clear Project
Update Project
Print Chart
Use Time Log
Use Defect Log
Import
Export

## Team
ID | Name | Initials | Phone | e-mail | Workbook Filename | Plan Tasks | Plan Hours | Plan Weeks
1 | Kimmo Airamaa | KA | 045-6335543 | kimmo.airamaa@helsinki.fi | kimmo2.xls
2 | Andreas Asuja | AA | 050-3495400 | andreas.asuja@helsinki.fi | andreas2.xls
3 | Mari Muuronen | MM | 050-3855527 | mari.muuronen@helsinki.fi | mari2.xls
4 | Seppo Pastila | SP | 040-7700455 | seppo.pastila@helsinki.fi | seppo2.xls
5 | Virve Taivaljärvi | VT | 040-5623777 | virve.taivaljarvi@helsinki.fi | virve2.xls
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
[6 empty] | 0 | 0 | 0
Make copies of workbook for team members
Consolidation Mode
Consolidate Plans

## Roles
Team Member Roles |  | Design | Implementation | Integration and Test
Team Leader | Seppo Pastila
Development Manager | Kimmo Airamaa
Planning Manager | Mari Muuronen
Quality/Process Manager | Virve Taivaljärvi
Support Manager | Andreas Asuja
Process Manager
Quality Manager
Support Manager
Test Manager

## Goals (hidden)
|  | Measures |  | Tracking
Stakeholders | Goal | Goal | Actual | Who | When

## SUMP
TSPi Plan Summary - Form SUMP
Name | Lohtu |  |  | Date | 2026-07-28 13:39
Team | B |  |  | Instructor | Inkeri Verkamo
Part/Level |  |  |  | Cycle | 2
Program Size | Plan | Actual
Total Requirements Pages (SRS) | 51 | 37
Total HLD Pages (SDS) | 40 | 37
Total Detailed Design Lines
Base LOC (B) | 1918 | 1933
Deleted LOC (D) | 150 | 0
Modified LOC (M) | 450 | 0
Added LOC (A) | 1750 | 817
Reused LOC (R) | 200 | 0
New and Changed LOC (N) | 2200 | 817
Total LOC (T) | 3718 | 2750
Total New Reuse LOC
Estimated Object LOC (E)
Upper Prediction Interval (70%)
Lower Prediction Interval (70%)
Time in Phase (hours) | Plan | Actual | Actual%
Management and Miscellaneous | 38 | 25 | 24.04%
Launch and Strategy | 0 | 0 | 0%
Planning | 0 | 0 | 0%
Requirements | 1 | 0 | 0%
System Test Plan | 1 | 1 | 0.9615%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 10 | 20 | 19.23%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 7 | 9 | 8.654%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 5 | 2 | 1.923%
DLD Inspection | 0 | 0 | 0%
Code | 36 | 40 | 38.46%
Code Review | 5 | 3 | 2.885%
Compile | 0 | 0 | 0%
Code Inspection | 0 | 0 | 0%
Unit Test | 3 | 0 | 0%
Build and Integration Test | 0 | 0 | 0%
System Test | 5 | 0 | 0%
Documentation | 0 | 0 | 0%
Postmortem | 11 | 4 | 3.846%
Total | 122 | 104 | 100%
Total Time UPI (70%)
Total Time LPI (70%)
Defects Injected | Plan | Actual | Actual%
Planning | 0 | 0 | 0%
Requirements | 0 | 0 | 0%
System Test Plan | 0 | 0 | 0%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 2.5 | 15 | 62.5%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 4.48 | 0 | 0%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 10 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 144 | 9 | 37.5%
Code Review | 0 | 0 | 0%
Compile | 0 | 0 | 0%
Code Inspection | 0 | 0 | 0%
Unit Test | 0.6 | 0 | 0%
Build and Integration Test | 0 | 0 | 0%
System Test | 0 | 0 | 0%
Total Development Defects Injected | 161.58 | 24 | 100%
Defects Removed | Plan | Actual | Actual%
Planning | 0 | 0 | 0%
Requirements | 0 | 0 | 0%
System Test Plan | 0 | 0 | 0%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 1.625 | 0 | 0%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 3.4808 | 15 | 62.5%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 8.312 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 73.7811 | 2 | 8.333%
Code Review | 0 | 0 | 0%
Compile | 0 | 0 | 0%
Code Inspection | 51.6468 | 0 | 0%
Unit Test | 20.4609 | 0 | 0%
Build and Integration Test | 1.8187 | 0 | 0%
System Test | 0.36375 | 7 | 29.17%
Total Development Defects Removed | 161.4891 | 24 | 100%
Post-Development | 0.090937
Product Life
Summary | Plan | Actual
LOC/Hour | 18.0328 | 7.8558
CPI (Cost-Performance Index)
% Reuse
% New Reuse

## SUMQ
TSPi Quality Plan - Form SUMQ
Name | Lohtu |  |  | Date | 2026-07-28 13:39
Team | B |  |  | Instructor | Inkeri Verkamo
Part/Level |  |  |  | Cycle | 2
SYSTEM Percent Defect Free |  |  | Actual
In Compile |  |  | 100%
In Unit Test |  |  | 100%
In Build and Integration Test |  |  | 100%
In System Test |  |  | 66.67%
In Acceptance Test
In Product Life
Defects/Page |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 0.087019 | 0.40541
Defects/KLOC |  | Plan | Actual
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 0 | 0
Compile |  | 0 | 0
Code Inspection |  | 23.4758 | 0
Unit Test |  | 9.3004 | 0
Build and Integration Test |  | 0.8267 | 0
System Test |  | 0.16534 | 8.5679
Total Development |  | 73.4041 | 29.3758
Acceptance Test |  | 0.041335 | 0
Product Life |  | 0 | 0
Total |  | 73.4455 | 29.3758
Defect Ratios |  | Plan | Actual
DLD Review/Unit Test |  | 0 | 0
Code Review/Compile |  | 0 | 0
Development Time Ratios |  | Plan | Actual
REQ Inspection/Requirements |  | 0 | 0
HLD Inspection/High-Level Design |  | 0.7 | 0.45
Detailed Design/Code |  | 0 | 0
DLD Review/Detailed Design |  | 0 | 0
Code Review/Code |  | 0.13889 | 0.075
Inspection/Review Rates |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 5.7143 | 4.1111
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 440 | 272.3333
Code Inspection |  | 0 | 0
A/FR |  | 1.6667 | 0
Phase Yields |  | Plan | Actual
Planning |  | 0% | 0%
Requirements |  | 0% | 0%
System Test Plan |  | 0% | 0%
REQ Inspection |  | 0% | 0%
High-Level Design |  | 65% | 0%
Integration Test Plan |  | 0% | 0%
HLD Inspection |  | 65% | 100%
Detailed Design |  | 0% | 0%
DLD Review |  | 0% | 0%
Test Development |  | 70% | 0%
DLD Inspection |  | 0% | 0%
Code |  | 50% | 22.22%
Code Review |  | 0% | 0%
Compile |  | 0% | 0%
Code Inspection |  | 70% | 0%
Unit Test |  | 90% | 0%
Build and Integration Test |  | 80% | 0%
System Test |  | 80% | 100%
Process Yields |  | Plan | Actual
% Before Compile |  | 54.17% | 70.83%
% Before Unit Test |  | 86.25% | 70.83%
% Before Build and Integration Test |  | 98.59% | 70.83%
% Before System Test |  | 99.72% | 70.83%
% Before Acceptance Test |  | 99.94% | 100%
Defect Injection Rates (Defects Injected Per Hour) |  | Plan | Actual
Planning |  | 0 | 0
Requirements |  | 0 | 0
System Test Plan |  | 0 | 0
REQ Inspection |  | 0 | 0
High-Level Design |  | 0.25 | 0.75
Integration Test Plan |  | 0 | 0
HLD Inspection |  | 0.64 | 0
Detailed Design |  | 0 | 0
DLD Review |  | 0 | 0
Test Development |  | 2 | 0
DLD Inspection |  | 0 | 0
Code |  | 4 | 0.225
Code Review |  | 0 | 0
Compile |  | 0 | 0
Code Inspection |  | 0.5 | 0
Unit Test |  | 0.2 | 0
Build and Integration Test |  | 0.02 | 0
System Test |  | 0 | 0
Defect Removal Rates |  | Plan | Actual
Planning |  | 0 | 0
Requirements |  | 0 | 0
System Test Plan |  | 0 | 0
REQ Inspection |  | 0 | 0
High-Level Design |  | 0.1625 | 0
Integration Test Plan |  | 0 | 0
HLD Inspection |  | 0.49725 | 1.6667
Detailed Design |  | 0 | 0
DLD Review |  | 0 | 0
Test Development |  | 1.6624 | 0
DLD Inspection |  | 0 | 0
Code |  | 2.0495 | 0.05
Code Review |  | 0 | 0
Compile |  | 0 | 0
Code Inspection |  | 0 | 0
Unit Test |  | 6.8203 | 0
Build and Integration Test |  | 0 | 0
System Test |  | 0.07275 | 0

## SUMS
TSPi Size Summary - Form SUMS
| Name | Lohtu
| Team | B
| Date | 2026-07-28 13:39
| Instructor | Inkeri Verkamo
| Cycle | 2 |  |  |  | Planned Size | [7 empty] | Actual Size | [7 empty] | Planned Defects Injected | [17 empty] | Actual Defects Injected | [17 empty] | Planned Defects Removed | [17 empty] | Actual Defects Removed | [17 empty] | Planned Time | [21 empty] | Actual Time
Part ID | Part Name | Assembly/Part | Part of | Owner | Size Measure | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem
1 | Projektisuunnitelma | A | SYSTEM | AA | Text Pages | 11 | 0 | 2 | 0 | 0 | 2 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 11 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Määrittelydokumentti | A | SYSTEM | AA | Req Pages | 9 | 0 | 2 | 0 | 0 | 2 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Suunnitteludokumentti | A | SYSTEM | AA | HLD Pages | 30 | 0 | 10 | 10 | 0 | 20 | 40 | 0 | 30 | 0 | 5 | 7 | 0 | 12 | 37 | [19 empty] | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Testaussuunnitelma | A | SYSTEM | AA | Text Pages | 10 | 0 | 2 | 5 | 0 | 7 | 15 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | HTML-koodi | A | SYSTEM | AA | LOC | 318 | 50 | 50 | 700 | 0 | 750 | 968 | 0 | 318 | 0 | 0 | 47 | 0 | 47 | 365 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Java-koodi | A | SYSTEM | AA | LOC | 1465 | 100 | 400 | 1000 | 200 | 1400 | 2565 | 0 | 1465 | 0 | 0 | 770 | 0 | 770 | 2235 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Tietokannanpäivitys/taulujen luonti | A | SYSTEM | AA | LOC | 135 | 0 | 0 | 50 | 0 | 50 | 185 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Loppuraportti | A | SYSTEM | AA | Text Pages | 6 | 0 | 0 | 10 | 0 | 10 | 16 | 0 | 6 | 0 | 0 | 1 | 0 | 1 | 7 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Task
TSPi Task Planning Template - Form TASK | [11 empty] | Total Plan Hours
Name | Lohtu | [10 empty] | 126
Team | B
Date | 2026-07-28 13:39
Instructor | Inkeri Verkamo
Cycle | 2 |  | Plan Hours by Role
Assembly | Phase | Task | Team Leader | Development Manager | Planning Manager | Quality/Process Manager | Support Manager | 0 | Total Resource Hours | Estimated Size | Size Measure | Rate (per Hr.) | Estimated Hours | Engrs | Plan Hours | Actual Hours | Actual Date | Actual Week | Earned Value | Cumulative EV | Cumulative Plan Hours | Plan Value |  | Plan Week | Plan Date
SYSTEM | MGMT | Projektisuunnitelman/aikataulujen päivitys | 1 | 0 | 2 | 0 | 0 | 0 | 3 | [5 empty] | 3 | 1.6833 |  |  |  |  | 3 | 2.381 | 2.381 | 1 | 2003-03-03
SYSTEM | REQ | Määrittelyn päivitys | 1 | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | [5 empty] | 4 | 0.79365 | 3.1746 | 1 | 2003-03-03
SYSTEM | HLD | Suunnittelun päivitys | 0 | 9.5 | 0 | 0 | 0 | 0 | 9.5 | [5 empty] | 9.5 | 20.0167 |  |  |  |  | 13.5 | 7.5397 | 10.7143 | 2 | 2003-03-10
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 7.5 | [5 empty] | 7.5 | 9.1333 |  |  |  |  | 21 | 5.9524 | 16.6667 | 2 | 2003-03-10
SYSTEM | STP | Testaussuunnitelman päivitys | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 1 | 1.25 |  |  |  |  | 22 | 0.79365 | 17.4603 | 2 | 2003-03-10
SYSTEM | HLD | Käyttötapausten päivitys | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | [5 empty] | 0.5 | [5 empty] | 22.5 | 0.39683 | 17.8571 | 2 | 2003-03-10
SYSTEM | HLD | Käyttöliittymän suunnittelu | 1 | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | [5 empty] | 23.5 | 0.79365 | 18.6508 | 2 | 2003-03-10
SYSTEM | MGMT | Viikkopalaverit | 7 | 3 | 3 | 4 | 3 | 0 | 20 | [5 empty] | 20 | 13.1667 |  |  |  |  | 43.5 | 15.873 | 34.5238 | 2 | 2003-03-10
SYSTEM | CODE | Java-koodaus | 5.5 | 5 | 9 | 3 | 0 | 0 | 22.5 | [5 empty] | 22.5 | 40.1 |  |  |  |  | 66 | 17.8571 | 52.381 | 3 | 2003-03-17
SYSTEM | CODE | Html/jsp-koodaus | 2 | 2 | 6 | 4.5 | 0 | 0 | 14.5 | [5 empty] | 14.5 | 0.75 |  |  |  |  | 80.5 | 11.5079 | 63.8889 | 3 | 2003-03-17
SYSTEM | CR | Koodin katselmointi | 1 | 1 | 1 | 1 | 1 | 0 | 5 | [5 empty] | 5 | 3.9 |  |  |  |  | 85.5 | 3.9683 | 67.8571 | 3 | 2003-03-17
SYSTEM | ST | Järjestelmätestaus | 2 | 2 | 1 | 0 | 0 | 0 | 5 | [5 empty] | 5 | [5 empty] | 90.5 | 3.9683 | 71.8254 | 4 | 2003-03-24
SYSTEM | UT | Yksikkötestaus | 0 | 2 | 1.5 | 0 | 0 | 0 | 3.5 | [5 empty] | 3.5 | [5 empty] | 94 | 2.7778 | 74.6032 | 4 | 2003-03-24
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 1 | 1 | 4.5 | 3 | 1 | 0 | 10.5 | [5 empty] | 10.5 | 4.75 |  |  |  |  | 104.5 | 8.3333 | 82.9365 | 4 | 2003-03-24
SYSTEM | MGMT | Yleinen projektin hallinta | 5 | 0 | 0 | 0 | 0 | 0 | 5 | [5 empty] | 5 | 7.4167 |  |  |  |  | 109.5 | 3.9683 | 86.9048 | 4 | 2003-03-24
SYSTEM | PM | Postmortem | 3 | 2 | 2 | 2 | 2 | 0 | 11 | [5 empty] | 11 | 4.75 |  |  |  |  | 120.5 | 8.7302 | 95.6349 | 4 | 2003-03-24
SYSTEM | TD | Sovellusympäristön hallinnointi | 1 | 3 | 0 | 0 | 1.5 | 0 | 5.5 | [5 empty] | 5.5 | 2.5833 |  |  |  |  | 126 | 4.3651 | 100 | 4 | 2003-03-24
0
Update Task and Schedule Plan
Generate Task List

## Schedule
TSPi Schedule Planning Template - Form SCHEDULE
| Name | Lohtu
| Team | B |  |  |  |  | Total Task Plan Hours | 126
| Date | 2026-07-28 13:39 |  |  |  |  | Total Schedule Plan Hours | 126
| Instructor | Inkeri Verkamo |  |  |  |  | Difference | 0
| Cycle | 2
Date | Week | Planned Hours | Cumulative Planned Hours | Actual Hours | Cumulative Actual Hours | Planned Value | Cumulative Planned Value | Earned Value | Cumulative EV | Predicted Hours | Cumulative Predicted Hours | Predicted Earned Value | Cumulative Predicted Earned Value
2003-03-03 | 1 | 10 | 10 | 11.9833 | 11.9833 | 3.1746 | 3.1746 | 0 | 0
2003-03-10 | 2 | 40 | 50 | 43.85 | 55.8333 | 31.3492 | 34.5238 | 0 | 0
2003-03-17 | 3 | 36 | 86 | 40.2667 | 96.1 | 33.3333 | 67.8571 | 0 | 0
2003-03-24 | 4 | 40 | 126 | 9.4833 | 105.5833 | 32.1429 | 100 | 0 | 0
2003-03-31 | 5 |  |  | 4.0833 | 109.6667 |  |  | 0 | 0
2003-04-07 | 6 |  |  | 0 | 109.6667 |  |  | 0 | 0
2003-04-14 | 7 |  |  | 0 | 109.6667 |  |  | 0 | 0
2003-04-21 | 8 |  |  | 0 | 109.6667 |  |  | 0 | 0
2003-04-28 | 9 |  |  | 0 | 109.6667 |  |  | 0 | 0

## Risk (hidden)
Risk | Impact | Likelihood | Priority | Assigned | Date

## LOGT
TSPi Time Recording Log - Form LOGT
Name | Lohtu |  |  | Date | 2026-07-28 13:39
Team | B |  |  | Instructor | Inkeri Verkamo
|  |  |  | Cycle | 2
Assembly | Phase | Task | Date | Start | Int. | Stop | Delta | Comments
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-09 | 20:00 |  | 20:30 | 30 | Suunnitteludokkarin lukeminen
SYSTEM | MGMT | Viikkopalaverit | 2003-03-10 | 10:03 |  | 11:13 | 70 | Projektikokous
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-10 | 11:15 |  | 12:05 | 50 | Suunnitteludokkarin katselmointi
SYSTEM | MGMT | Sovellusympäristön hallinnointi | 2003-03-10 | 12:45 |  | 15:20 | 155 | Tomcatin virittelyä
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-12 | 9:30 |  | 10:00 | 30 | Pöytäkirjojen konvertointia ja nettisivujen päivitystä
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-10 | 8:00 |  | 10:00 | 120 | Ekan syklin postmortem
SYSTEM | MGMT | Viikkopalaverit | 2003-03-10 | 10:00 |  | 12:00 | 120 | Tokan syklin eka palaveri
SYSTEM | CODE | Java-koodaus | 2003-03-10 | 12:30 |  | 17:10 | 279.5 | Ekan syklin koodin korjailua ja testausta
SYSTEM | CODEINSP | Koodin katselmointi | 2003-03-16 | 19:10 |  | 19:20 | 10 | Ekan syklin koodin katselmointi
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-16 | 19:20 |  | 19:30 | 10 | Viikkorapostti ja agnda maanantain palaverille
SYSTEM | CODE | Java-koodaus | 2003-03-16 | 19:30 |  | 23:30 | 240 | Checkstyle virheet pois ja ekan syklin virheiden selvittelyä
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-16 | 23:30 |  | 23:50 | 20 | Suunniteludokumentin katselmointi
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-17 | 8:05 |  | 9:03 | 58 | Suunniteludokumentin katselmointi
SYSTEM | MGMT | Viikkopalaverit | 2003-03-17 | 9:03 |  | 9:50 | 47 | Tokan syklin toka palaveri
SYSTEM | CODE | Java-koodaus | 2003-03-17 | 9:50 |  | 12:00 | 130 | Ekan syklin koodin korjailua ja testausta
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-17 | 12:00 |  | 12:30 | 30 | Palaveri Verkamon kanssa.
SYSTEM | CODE | Java-koodaus | 2003-03-17 | 13:00 |  | 18:00 | 300 | Ekan syklin koodin korjailua ja testausta
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-30 | 16:00 |  | 18:00 | 120 | Loman jälkeinen kiinni otto ja postmortem valmistelu
SYSTEM | MGMT | Postmortem | 2003-04-01 | 8:00 |  | 9:00 | 60 | Tokan syklin postmortem
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-07 | 14:30 |  | 16:55 | 145 | suunnittelua
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-09 | 10:05 |  | 15:15 | 310 | Suunnittelua
SYSTEM | MGMT | Viikkopalaverit | 2003-03-10 | 8:00 |  | 12:00 | 240 | FTR & postmortem & projektikokous
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-11 | 14:00 |  | 15:50 | 110 | suunnitteludokumentin säätämistä & UML
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-12 | 13:00 |  | 14:05 | 65 | Suunnitteludokumentin päivittämistä
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-13 | 7:25 |  | 8:09 | 44 | suunnitteludokumentin kyhäämistä
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-14 | 9:16 |  | 10:02 | 45.2 | Toiminnan selvittämistä & sekvenssikaavioiden säätöä
SYSTEM | CR | Koodin katselmointi | 2003-03-13 | 15:00 |  | 18:45 | 225 | Koodikatselmointikorjausten tekemistä & javadoc
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-14 | 11:26 |  | 12:09 | 43.35 | Sekvenssikaavioita (onko enää ihme)
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-16 | 12:07 |  | 14:45 | 158 | Viimeisen (tarpeettoman) sekvenssikaavion viilausta
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-17 | 11:00 |  | 11:48 | 48.15 | Suunnitteludokumentin päivittämistä
SYSTEM | CODE | Java-koodaus | 2003-03-18 | 17:50 |  | 18:26 | 36 | Koodausta
SYSTEM | CODE | Java-koodaus | 2003-03-19 | 9:45 |  | 10:12 | 27.4833 | Koodausta
SYSTEM | CODE | Java-koodaus | 2003-03-19 | 11:15 |  | 13:46 | 151.3 | Koodausta (taas kerran)
SYSTEM | CODE | Java-koodaus | 2003-03-19 | 13:49 |  | 15:16 | 86.8167 | Koodausta ja luokkien korjailuita (pääosin korjailua)
SYSTEM | CODE | Java-koodaus | 2003-03-20 | 13:40 |  | 15:55 | 135 | koodausta
SYSTEM | CODE | Java-koodaus | 2003-03-21 | 12:57 |  | 14:35 | 98 | koodausta ja viilausta
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-22 | 10:00 |  | 12:35 | 155 | suunnittelun päivitystä, UML-säätämistä
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-23 | 12:00 |  | 12:34 | 33.7667 | Niitä hiivatin sekvenssikaavioita ja Rational Rosea (RR hirteen!)
SYSTEM | CODE | Java-koodaus | 2003-03-27 | 8:50 |  | 9:25 | 35 | Koodausta
SYSTEM | HLD | Suunnittelun päivitys | 2003-03-06 | 14:15 |  | 15:00 | 45 | suunnittelusta spostittelua
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-09 | 17:10 |  | 17:40 | 30 | suunnitteludokumentin katselmointia
SYSTEM | MGMT | Viikkopalaverit | 2003-03-10 | 10:03 |  | 11:13 | 70 | viikkopalaveri
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-10 | 11:13 |  | 12:05 | 52 | suunnitteludokumentin katselmointi
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-10 | 14:10 |  | 14:45 | 35 | katselmointidokkarin kirjoitus
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-10 | 14:45 |  | 15:20 | 35 | prjkokouksen pk
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-10 | 21:15 |  | 21:50 | 35 | prjkokouksen pk:n päivitys + pöytäkirjojen kopiointia
SYSTEM | CODE | Html/jsp-koodaus | 2003-03-12 | 11:20 |  | 11:50 | 30 | menun ja kehysten etsintä + korjattu kuva suunnitteludokkariin
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-13 | 13:45 |  | 13:54 | 9.4333 | tuntien kirjaus
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-14 | 16:30 |  | 16:55 | 25 | TSP-laatuarvioita
SYSTEM | STP | Testaussuunnitelman päivitys | 2003-03-14 | 17:25 |  | 17:30 | 5 | Testitapausten tarkistus
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-15 | 16:40 |  | 17:05 | 25 | Suunnitteludokumentin katselmointi
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-17 | 8:00 |  | 9:00 | 60 | Suunnitteludokumentin katselmointi
SYSTEM | MGMT | Viikkopalaverit | 2003-03-17 | 9:00 |  | 9:50 | 50 | viikkopalaveri
SYSTEM | CODE | Java-koodaus | 2003-03-17 | 9:50 |  | 10:45 | 55 | Koodin ihmettelyä
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-17 | 11:45 |  | 12:10 | 25 | katselmointidokkarin kirjoitus
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-17 | 12:10 |  | 12:45 | 35 | prjkokouksen pk
SYSTEM | STP | Testaussuunnitelman päivitys | 2003-03-17 | 12:50 |  | 14:00 | 70 | Testitapausten päivitys
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-20 | 14:20 |  | 14:40 | 20 | Päivitetty SUMQ ja LOGD
SYSTEM | CODE | Java-koodaus | 2003-03-20 | 14:50 |  | 16:50 | 120 | UserVO- ja TaskVO-luokkien koodausta
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-21 | 11:50 |  | 12:00 | 10 | tuntien kirjaus
SYSTEM | MGMT | projektikokouksen valmistelu | 2003-03-24 | 19:50 |  | 20:00 | 10 | vt-propän hommia
SYSTEM | MGMT | Viikkopalaverit | 2003-03-26 | 14:00 |  | 14:45 | 45 | viikkopalaveri + ihmettelyä päälle
SYSTEM | CODE | Java-koodaus | 2003-03-26 | 15:10 |  | 16:05 | 55 | TaskVO-luokan koodausta
SYSTEM | CODE | Html/jsp-koodaus | 2003-03-29 | 18:40 |  | 18:55 | 15 | alustavaa aikaisemman jsp-sivun tutkimista
SYSTEM | PM | Postmortem | 2003-03-29 | 19:10 |  | 19:50 | 40 | vertaisarviointi ja syklin miettimistä
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-30 | 13:20 |  | 13:30 | 10 | tuntien kirjaus
SYSTEM | PM | Postmortem | 2003-03-31 | 18:31 | 24 | 20:15 | 80 | laaturaportti postmortemiin
SYSTEM | PM | Postmortem | 2003-04-01 | 8:15 |  | 9:00 | 45 | Postmortem
SYSTEM | MGMT | Projektisuunnitelman/aikataulujen päivitys | 2003-03-06 | 15:36 |  | 16:02 | 26.0333 | 2.syklin aikataulujen suunnittelu
SYSTEM | MGMT | Projektisuunnitelman/aikataulujen päivitys | 2003-03-06 | 18:15 |  | 19:31 | 75.8833 | 2.syklin TSP-työkalun valmistelu
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-09 | 20:30 |  | 21:29 | 59.05 | 2.syklin TSP-työkalun valmistelu
SYSTEM | MGMT | Viikkopalaverit | 2003-03-10 | 10:00 |  | 11:00 | 60 | 2. syklin 1. vkopalaveri
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-10 | 11:00 |  | 11:45 | 45
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-10 | 16:00 |  | 16:30 | 30 | aikataulujen tekeminen
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-13 | 19:30 |  | 20:08 | 38.3667 | viikkotuntien kirjaus
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-15 | 13:00 |  | 13:30 | 29.8 | tuntiyhteenvedon tekeminen
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-16 | 17:30 |  | 18:30 | 60 | suunnitteludokumentin lukeminen
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-16 | 18:30 |  | 18:48 | 17.5667 | tuntiyhteenvedon tekeminen
SYSTEM | MGMT | Viikkopalaverit | 2003-03-17 | 8:00 |  | 9:00 | 60 | 2. syklin 2. vkopalaveri
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 2003-03-17 | 9:00 |  | 10:00 | 60
SYSTEM | CODE | Java-koodaus | 2003-03-17 | 10:00 |  | 12:00 | 120 | 1.syklin testausta
SYSTEM | CODE | Java-koodaus | 2003-03-18 | 17:00 |  | 20:00 | 180 | 1.syklin testausta
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-23 | 14:37 | 20 | 15:16 | 18.6833
SYSTEM | CODE | Java-koodaus | 2003-03-23 | 15:01 |  | 17:32 | 150.8833 | 1.syklin testausta
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-03-23 | 18:39 |  | 19:00 | 20.9667 | viikkoyhteenvedon tekeminen
SYSTEM | CODE | Java-koodaus | 2003-03-23 | 19:00 |  | 19:30 | 29.6333 | 2.syklin luokkien rungon tekeminen
SYSTEM | MGMT | Viikkopalaverit | 2003-03-26 | 14:00 |  | 14:30 | 30 | 2.syklin 3.vkopalaveri
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-03-26 | 14:30 |  | 15:00 | 30
SYSTEM | CODE | Java-koodaus | 2003-03-27 | 18:00 |  | 21:00 | 180
SYSTEM | MGMT | Postmortem | 2003-03-31 | 20:37 |  | 21:37 | 60.1167

## LOGD
TSPi Defect Recording Log - Form LOGD
Name | Lohtu |  |  | Date | 2026-07-28 13:39
Team | B |  |  | Instructor | Inkeri Verkamo
|  |  |  | Cycle | 2
Date | Num | Type | Assembly | Injected | Removed | Fix Time | Fix Ref. | Description
2003-03-10 | 1 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Ohjelman nimi pois Projektin perustiedot sivulta
2003-03-10 | 2 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | LohtuResources-luokan metodit setLogFileName ja setLogLevel yhdistyvät yhdeksi setLogger-metodiksi. (s. 19)
2003-03-10 | 3 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Luvun 3.4 alle lisättävä aliluvut PhaseVO, PhaseDAO, UsersTasksVO ja UsersTaskDAO-luokille
2003-03-10 | 4 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Luvun 3.6 alle lisättävä aliluku uudelle kontroller-luokalle. CycleController
2003-03-10 | 5 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Lukuun 3.7.1 lisättävä tiedot uudesta CyclePlanning.jsp-sivusta sekä vasemman reunan navigointipalkista.
2003-03-10 | 6 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Vaihdetaan lukujen 3.7 ja 3.8 paikkoja
2003-03-10 | 7 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuvan 17 PhaseVO-luokkaan muutetaan jokainen ajanhakumetodi palauttamaan Date-olion sekä näille rinnakkaismetodit, jotka palauttavat String-oliot
2003-03-10 | 8 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Muutetaan LohtuResources ja LohtuInit-luokkia siten, että LohtuInit asettaa LohtuResources-luokalle käytetyn aikaleiman muodon.LohtuResources-luokkaan lisätään myös uusi metodi, joka palauttaa SimpleFormatter-olion.
2003-03-10 | 9 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuvan 17 PhaseVO-luokan isDeleted-metodi puuttuu
2003-03-10 | 10 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuva 18 poistetaan
2003-03-10 | 11 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuvassa 19 puuttuvat metodien parametrit ja palautusarvot
2003-03-10 | 12 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuvan 19 TaskVO-luokkaan muutetaan jokainen ajanhakumetodi palauttamaan Date-olion sekä lisätään näille rinnakkaismetodit, jotka palauttavat String-olion
2003-03-10 | 13 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuva 20 poistetaan
2003-03-10 | 14 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuvaa 21 lisätään ohjelman osien ja projektiryhmäläisten hakeminen sivulle
2003-03-10 | 15 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Syklin suunnittelusivulla olevat poistot kuvataan omissa sekvenssikaavioissaan
2003-03-23 | 16 | 80 | Java-koodi | CODE | ST |  |  | ProjectDAO: väärän niminen sarake tietokantakyselyssä
2003-03-23 | 17 | 80 | Java-koodi | CODE | ST |  |  | ProjectDAO: väärän niminen sarake tietokantakyselyssä
2003-03-23 | 18 | 80 | Java-koodi | CODE | ST |  |  | ProjectDAO: väärän niminen sarake tietokantakyselyssä
2003-03-23 | 19 | 80 | Java-koodi | CODE | ST |  |  | ComponentDAO: tarkistus if (component.getId() <= 0 ) turha
2003-03-23 | 20 | 80 | Java-koodi | CODE | ST |  |  | processmodel lisäys, id:tä ei saa lisätä itse
2003-03-23 | 21 | 80 | Java-koodi | CODE | ST |  |  | ProcessmodelDAO: väärän niminen sarake tietokantakyselyssä
2003-03-23 | 22 | 80 | Java-koodi | CODE | ST |  |  | ProcessmodelDAO: lohko suljetaan väärässä kohtaa
2003-03-26 | 23 | 40 | Java-koodi | CODE | CODE |  |  | puuttui Date-luokan importointi TaskVO:sta
2003-03-26 | 24 | 40 | Java-koodi | CODE | CODE |  |  | getActualDeadline-metodi kahdesti, ku olin Stringin palauttavaan metodiin unohtanu laittaa S:n perään...
2003-03-17 | 25 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Lukuun 1.5.2 lisätään maininta, ettei suure-kenttiä toteuteta syklissä 2.
2003-03-17 | 26 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuva 11: LohtuResources-luokasta puuttuvat metodit setDateFormatter ja formatDate. Lisäksi setLogFileName- ja setLogLevel-metodit pitää korvata setLogger-metodilla.
2003-03-17 | 27 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuva 13: PhaseDAO-luokan konstruktorista poistettava ”= default”-teksti.
2003-03-17 | 28 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuva 15: LohtuResources-luokasta puuttuvat metodit setDateFormatter ja formatDate. Lisäksi setLogFileName-metodi pitää korvata setLogger-metodilla.
2003-03-17 | 29 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | 3.6.1-luvussa ProjectController-luokan kuvausta tarkennetaan: kyseinen luokka ohjaa projektin perustietosivun toimintoja.
2003-03-17 | 30 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | 3.6.2-luvusta poistetaan tieto, jonka mukaan toiminto toteutettaisiin toisessa syklissä.
2003-03-17 | 31 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuva 16 poistetaan.
2003-03-17 | 32 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Luvusta 3.7.1 poistetaan viittaus kuvaan 16.
2003-03-17 | 33 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Luvusta 3.9 poistetaan teksti ”syklin 1 toteutettavissa”.
2003-03-17 | 34 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuva 20: DAOFactoryn ja PhaseDAOn väliin lisättävä CyclePlannin.jsp-sivu, joka hoitaa getDAOt, –Iteratorit jne kuten kuvassa 17.
2003-03-17 | 35 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuvista 20, 21 ja 22 poistetaan Asiakkaasta maininta jsp:stä.
2003-03-17 | 36 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuva 21: Lisätään Iteratoreista kommentti, että niitä käytetään tarkistusten tekemiseen. Lisätään myös olemassaolevien vaiheiden ja tehtävien päivityksen kuvaus.
2003-03-17 | 37 | 10 | Suunnitteludokumentti | HLD | HLDINSP |  |  | Kuvan 22 yhteyteen maininta siitä, että aina poistoja suoritettaessa suoritetaan myös kuvassa 21 esitetyt toiminnot. Lisätään myös seuraavankaltainen kommentti: ”Tehtävien poisto tapahtuu vastaavalla tavalla kuin vaiheiden poisto. Syklin poistoa ei toistaiseksi ole suunniteltu.”

## Week
TSPi Week Summary - Form WEEK
Name | Lohtu |  | Date | 2026-07-28 13:39
Team | B |  | Instructor | Inkeri Verkamo
Week | 6 |  | Cycle | 2
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 0 | 0
Project hours this cycle to date |  |  | 0 | 109.6667
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
0
Totals | 0 | 0 | 0 | 0
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week

## DefectTypes
Type | Description
10 | Documentation
20 | Syntax
30 | Build, Package
40 | Assignment
50 | Interface
60 | Checking
70 | Data
80 | Function
90 | System
100 | Environment

## Phases (hidden)
Phase | Description | Task Generator S-System P-Part N-None | LOGT Track Time | LOGD Track Defects Injected | LOGD Track Defects Removed | PDF | DefDen | DefRatios | DevTimeRatio | RvwRate | PhaseYld | ProcYld | DI Rate | DR Rate
MGMT | Management and Miscellaneous | S | Y | N | N | N | N |  |  | N | N | N | N | N
STRAT | Launch and Strategy | S | Y | N | N | N | N |  |  | N | N | N | N | N
PLAN | Planning | S | Y | Y | Y | N | N |  |  | N | Y | Y | Y | Y
REQ | Requirements | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
STP | System Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
REQINSP | REQ Inspection | S | Y | Y | Y | N | Y |  | Requirements | Y | Y | N | Y | Y
HLD | High-Level Design | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
ITP | Integration Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
HLDINSP | HLD Inspection | S | Y | Y | Y | N | Y |  | High-Level Design | Y | Y | N | Y | Y
DLD | Detailed Design | P | Y | Y | Y | N | N |  | Code | N | Y | N | Y | Y
DLDR | DLD Review | P | Y | Y | Y | N | Y | Unit Test | Detailed Design | Y | Y | N | Y | Y
TD | Test Development | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
DLDINSP | DLD Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
CODE | Code | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
CR | Code Review | P | Y | Y | Y | N | Y | Compile | Code | Y | Y | N | Y | Y
COMPILE | Compile | P | Y | Y | Y | y | Y |  |  | N | Y | Y | Y | Y
CODEINSP | Code Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
UT | Unit Test | P | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
IT | Build and Integration Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
ST | System Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
DOC | Documentation | S | Y | N | N | N | N |  |  | N | N | N | N | N
PM | Postmortem | S | Y | N | N | N | N |  |  | N | N | N | N | N
AT | Acceptance Test | N | N | N | Y | Y | Y |  |  | N | N | Y | N | N
PL | Product Life | N | N | N | Y | Y | Y |  |  | N | N | N | N | N
Copyright 1998 James W. Over

## QProfParam
Parameter | Value | Description
Design/Code Time | 50% | Design time as % of coding time
Code Review Time | 50% | Code review time as % of code time
Compile Defects/KLOC | 10 | Compile defects/KLOC
Unit Test Ddefects/KLOC | 5 | Unit test defects/KLOC
Design Review Time | 50% | Design review time as % of design time
Restore Qprofile Parameter Defaults