## Index (hidden)
TSPe Support Tool Index of Forms and Charts
FORMS | Description | CHARTS | Description
Launch Meeting/Planning Forms |  | Earned Value | Planned vs. earned value and projected earned value
Use these forms to plan a new project or build |  | Plan vs. Actual Hours | Planned vs. actual hours
Project | Project startup and summary form | Defect Removal Profile | Defects removed by phase for each component
Team | Team member summary | Quality Profile
Roles | TSPe role assignments | Percent Defect Free | Percent of components that are defect free by phase
Goals | Team goals
Components | Product component list
Task | Task plan template
Schedule | Schedule plan template
QUAL-Plan | Quality plan for system and components
COMPR-Plan | Resource plan for system and components
COMPD-Plan | Defect injection/removal plan for system and components
Risks | Team risk assessment
Weekly Meeting/Tracking Forms
Use these forms for gathering data and tracking a project or build
TimeLog | Time recording Log
DefectLog | Defect recording log
Week | Weekly meeting status report
Task | Task plan template
Schedule | Schedule plan template
QUAL-Actual | Quality actuals for system and components
COMPR-Actual | Resource actuals for system and components
COMPD-Actual | Defects injected/removed for system and components
Standards
Phases | TSPe process phase standard
DefectTypes | Defect type standard
Copyright 1998 James W. Over

## Instructions
TSPi Support Tool Instructions
Strategy Development and Planning
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
Before STRAT1 | Team Leader | Fill out the project information on the Project worksheet (Name, Team name, Project name, Start Date, Instructor, Cycle). | Project!Name
Before STRAT1 | Team Leader | Enter the team member names, initials, phone numbers, e-mail addresses, and filenames for the team members workbooks in the Team worksheet. | Team!B2
Before STRAT1 | Team Leader | Enter the role assignments on the Roles worksheet. | Roles!B2
STRAT: Establish Team Goals | Planning Manager | Enter the team goals on the Goals worksheet | Goals!B3
STRAT1: Produce the Size Estimate | Planning Manager | Enter on the SUMS worksheet, the names and size estimates of all assemblies and parts for this cycle. | SUMS!B8
PLAN1: Produce the Task Plan | Planning Manager | Click the Generate Task List button to create a default task list. | Task!A8
PLAN1: Produce the Task Plan | Planning Manager | Revise the task list adding or deleting tasks as necessary. Then for each task, estimate the size where appropriate, the time, and the time for each engineer assigned to the task. | Task!A8
PLAN1: Produce the Schedule Plan | Planning Manager | Enter hours per week in the Schedule template. Hours per week are based on the total hours for the team for each week in the schedule. | Schedule!C8
| Planning Manager | Click the Update Task and Schedule Plan button on the Task Worksheet to generate a schedule. | Task!A8
PLAN1: Quality Plan | Team | Before creating the quality plan, review the quality standard in the textbook.
PLAN1: Quality Plan | Quality/Process Manager | Enter the planned defect injection rates for each phase on the SUMQ worksheet. | SUMQ!D82
PLAN1: Quality Plan | Quality/Process Manager | Enter estimated phase yields for each phase. | SUMQ!D55
PLAN1: Quality Plan | Team | Review the calculated defect removal rates and defect densities (Defects/KLOC) against the Quality Standard. If necessary, adjust planned time (Task worksheet), defect injection rates (SUMQ), or defect removal yields (SUMQ).
PLAN: Balance Workload | Planning Manager | Make 1 copy of the team workbook for each engineer. Use the filename entered on the Team worksheet (Workbook Filename). Click the Make copies... button to create the copies automatically. | Team!B2
PLAN: Balance Workload | Each engineer | Revise the tasks in the Task worksheet to reflect the individual engineers workload (e.g. delete task not assigned to you, and where you share an assignment with other engineers, set their planned hours to zero). | Task!A8
PLAN: Balance Workload | Each engineer | Revise the schedule plan on the Schedule worksheet to reflect your available hours per week. | Schedule!C8
PLAN: Balance Workload | Planning Manager | Load the engineers' individual worksheets and the consolidated team plan workbook into the same folder. Open the consolidated team plan workbook. Click the consolidate plan button on the Team worksheet to build a consolidated plan | Team!B2
PLAN: Balance Workload | All team members | If necessary, reassign tasks to balance the workload and repeat the previous 3 steps until a balanced plan is achieved. If planned times for any task change, review the quality plan and revise it if necessary.
Weekly Tracking
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
STRAT, PLAN, REQ, DES, IMP, TEST, PM | All team members | During all TSPi phases, use the time log to record data on each task. Include the assembly and phase for each task, the date, start time, interrupt time, stop time, and comments. | LOGT!A7
REQ, DES, IMP, TEST | All team members | During TSPi phases REQ, DES, IMP, and TEST, use the defect log to record data on each defect. Include the date, number, type, assembly, phase injected, phase removed, fix time, fix reference, and description | LOGD!A7
Weekly | All team members | Click the Update Project button on the Project worksheet to update individual plans. Print the Task and Schedule worksheets. | Project!Name
Weekly | All team members | Print the Task worksheet. | Task!A8
Weekly | All team members | Print the Schedule worksheet. | Schedule!A8
Weekly | All team members | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | All team members | Send a copy of your workbook to the planning manager for use in preparing the team's consolidated weekly report.
Weekly | Planning Manager | Update consolidated team plan with the current week's data and prepare status reports for the weekly meeting.
Weekly | Planning Manager | Load the individual engineers workbooks and the consolidated team workbook into the same folder. Open the consolidated team workbook. Click the Consolidate Plans button on Team worksheet to update consolidated team plan with the current week's data. | Team!F1
Weekly | Planning Manager | Select the Project worksheet and click the update project button before printing status reports for the weekly meeting. | Project!Name
Weekly | Planning Manager | Print the Task worksheet. | Task!A8
Weekly | Planning Manager | Print the Schedule worksheet. | Schedule!A8
Weekly | Planning Manager | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Earned Value -Plan vs. Actual Hours | Project!Name
Weekly during implementation and testing phases | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Defect Removal Profile -Quality Profile -Percent Defect Free | Project!Name
Project and Cycle Postmortem
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
PM | All team members | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | All team members | Select the Project worksheet and click the export button to save a copy of your data for the cycle. | Project!Name
PM | Planning Manager | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | Planning Manager | Select the SUMP worksheet and print a SUMP form for the SYSTEM and each assembly | SUMP!B2
PM | Planning Manager | Select the SUMQ worksheet and print a SUMQ form for the SYSTEM and each assembly | SUMQ!B2
PM | Planning Manager | Select the SUMS worksheet and print a SUMS form | SUMS!B8
PM | Planning Manager | Select the Project worksheet and click the export button to save a copy of the consolidated team data for the cycle. | Project!Name

## Project
TSPi | - Project Summary |  |  | Design/Code Time | 1
|  |  |  | Code Review Time | 1
Name | Lohtu | Date | 2026-07-29 19:52 | Compile Defects/KLOC | 1
Project | Lohtu-projekti | Start Date | 2003-04-01 | Unit Test Ddefects/KLOC | 1
Team | B | Instructor | Inkeri Verkamo | Design Review Time | 1
Part/Level |  | Cycle | 3 | CR | 10.4167
|  | Today's Date Override |  | COMPILE | 3.4722
Version: | TSPi.19990907. Copyright 1999 Addison Wesley . |  |  | CODEINSP | 2.7778
|  |  |  | UT | 2.0833
|  |  |  | IT | 0
|  |  |  | ST | 0
|  |  |  | 1 Year | 0
|  |  |  | Product Life | 0
Draw Chart
Clear Project
Update Project
Print Chart
Use Time Log
Use Defect Log
Import
Export

## Team
ID | Name | Initials | Phone | e-mail | Workbook Filename | Plan Tasks | Plan Hours | Plan Weeks
1 | Kimmo Airamaa | KA | 045-6335543 | kimmo.airamaa@helsinki.fi | kimmo3.xls
2 | Andreas Asuja | AA | 050-3495400 | andreas.asuja@helsinki.fi | andreas3.xls
3 | Mari Muuronen | MM | 050-3855527 | mari.muuronen@helsinki.fi | mari3.xls
4 | Seppo Pastila | SP | 040-7700455 | seppo.pastila@helsinki.fi | seppo3.xls
5 | Virve Taivaljärvi | VT | 040-5623777 | virve.taivaljarvi@helsinki.fi | virve3.xls
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
[6 empty] | 0 | 0 | 0
Make copies of workbook for team members
Consolidation Mode
Consolidate Plans

## Roles
Team Member Roles |  | Design | Implementation | Integration and Test
Team Leader | Kimmo Airamaa
Development Manager | Seppo Pastila
Planning Manager | Mari Muuronen
Quality/Process Manager | Virve Taivaljärvi
Support Manager | Andreas Asuja
Process Manager
Quality Manager
Support Manager
Test Manager

## Goals (hidden)
|  | Measures |  | Tracking
Stakeholders | Goal | Goal | Actual | Who | When

## SUMP
TSPi Plan Summary - Form SUMP
Name | Lohtu |  |  | Date | 2026-07-29 19:52
Team | B |  |  | Instructor | Inkeri Verkamo
Part/Level |  |  |  | Cycle | 3
Program Size | Plan | Actual
Total Requirements Pages (SRS) | 47 | 37
Total HLD Pages (SDS) | 37 | 37
Total Detailed Design Lines
Base LOC (B) | 2735 | 2735
Deleted LOC (D) | 150 | 0
Modified LOC (M) | 450 | 0
Added LOC (A) | 1700 | 2273
Reused LOC (R) | 200 | 0
New and Changed LOC (N) | 2150 | 2273
Total LOC (T) | 4485 | 5008
Total New Reuse LOC
Estimated Object LOC (E)
Upper Prediction Interval (70%)
Lower Prediction Interval (70%)
Time in Phase (hours) | Plan | Actual | Actual%
Management and Miscellaneous | 62 | 36.7939 | 29.75%
Launch and Strategy | 0 | 0 | 0%
Planning | 0 | 0 | 0%
Requirements | 2 | 0.5 | 0.4043%
System Test Plan | 1 | 0.16667 | 0.1348%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 5 | 0 | 0%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 5 | 0 | 0%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 5 | 10.05 | 8.127%
DLD Inspection | 0 | 0 | 0%
Code | 58 | 62.8975 | 50.86%
Code Review | 25 | 0 | 0%
Compile | 0 | 0 | 0%
Code Inspection | 0 | 0 | 0%
Unit Test | 25 | 6 | 4.852%
Build and Integration Test | 0 | 0 | 0%
System Test | 25 | 7.25 | 5.863%
Documentation | 0 | 0 | 0%
Postmortem | 15 | 0 | 0%
Total | 228 | 123.6581 | 100%
Total Time UPI (70%)
Total Time LPI (70%)
Defects Injected | Plan | Actual | Actual%
Planning | 0 | 0 | 0%
Requirements | 0 | 0 | 0%
System Test Plan | 0 | 0 | 0%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 1.25 | 3 | 8.824%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 3.2 | 0 | 0%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 10 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 232 | 29 | 85.29%
Code Review | 0 | 0 | 0%
Compile | 0 | 0 | 0%
Code Inspection | 0 | 0 | 0%
Unit Test | 5 | 0 | 0%
Build and Integration Test | 0 | 0 | 0%
System Test | 0 | 2 | 5.882%
Total Development Defects Injected | 251.45 | 34 | 100%
Defects Removed | Plan | Actual | Actual%
Planning | 0 | 0 | 0%
Requirements | 0 | 0 | 0%
System Test Plan | 0 | 0 | 0%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 0.8125 | 0 | 0%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 2.3644 | 0 | 0%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 7.8912 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 117.691 | 25 | 73.53%
Code Review | 0 | 0 | 0%
Compile | 0 | 3 | 8.824%
Code Inspection | 82.3837 | 0 | 0%
Unit Test | 36.2766 | 4 | 11.76%
Build and Integration Test | 3.2246 | 0 | 0%
System Test | 0.64492 | 2 | 5.882%
Total Development Defects Removed | 251.2888 | 34 | 100%
Post-Development | 0.16123
Product Life
Summary | Plan | Actual
LOC/Hour | 9.4298 | 18.3813
CPI (Cost-Performance Index)
% Reuse
% New Reuse

## SUMQ
TSPi Quality Plan - Form SUMQ
Name | Lohtu |  |  | Date | 2026-07-29 19:52
Team | B |  |  | Instructor | Inkeri Verkamo
Part/Level |  |  |  | Cycle | 3
SYSTEM Percent Defect Free |  |  | Actual
In Compile |  |  | 66.67%
In Unit Test |  |  | 66.67%
In Build and Integration Test |  |  | 100%
In System Test |  |  | 66.67%
In Acceptance Test
In Product Life
Defects/Page |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 0.063902 | 0
Defects/KLOC |  | Plan | Actual
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 0 | 0
Compile |  | 0 | 1.3198
Code Inspection |  | 38.318 | 0
Unit Test |  | 16.8728 | 1.7598
Build and Integration Test |  | 1.4998 | 0
System Test |  | 0.29996 | 0.87989
Total Development |  | 116.8785 | 14.9582
Acceptance Test |  | 0.07499 | 0
Product Life |  | 0 | 0
Total |  | 116.9535 | 14.9582
Defect Ratios |  | Plan | Actual
DLD Review/Unit Test |  | 0 | 0
Code Review/Compile |  | 0 | 0
Development Time Ratios |  | Plan | Actual
REQ Inspection/Requirements |  | 0 | 0
HLD Inspection/High-Level Design |  | 1 | 0
Detailed Design/Code |  | 0 | 0
DLD Review/Detailed Design |  | 0 | 0
Code Review/Code |  | 0.43103 | 0
Inspection/Review Rates |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 7.4 | 0
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 86 | 0
Code Inspection |  | 0 | 0
A/FR |  | 1 | 0
Phase Yields |  | Plan | Actual
Planning |  | 0% | 0%
Requirements |  | 0% | 0%
System Test Plan |  | 0% | 0%
REQ Inspection |  | 0% | 0%
High-Level Design |  | 65% | 0%
Integration Test Plan |  | 0% | 0%
HLD Inspection |  | 65% | 0%
Detailed Design |  | 0% | 0%
DLD Review |  | 0% | 0%
Test Development |  | 70% | 0%
DLD Inspection |  | 0% | 0%
Code |  | 50% | 78.12%
Code Review |  | 0% | 0%
Compile |  | 0% | 42.86%
Code Inspection |  | 70% | 0%
Unit Test |  | 90% | 100%
Build and Integration Test |  | 80% | 0%
System Test |  | 80% | 100%
Process Yields |  | Plan | Actual
% Before Compile |  | 52.25% | 78.12%
% Before Unit Test |  | 85.67% | 87.5%
% Before Build and Integration Test |  | 98.4% | 100%
% Before System Test |  | 99.68% | 100%
% Before Acceptance Test |  | 99.94% | 100%
Defect Injection Rates (Defects Injected Per Hour) |  | Plan | Actual
Planning |  | 0 | 0
Requirements |  | 0 | 0
System Test Plan |  | 0 | 0
REQ Inspection |  | 0 | 0
High-Level Design |  | 0.25 | 0
Integration Test Plan |  | 0 | 0
HLD Inspection |  | 0.64 | 0
Detailed Design |  | 0 | 0
DLD Review |  | 0 | 0
Test Development |  | 2 | 0
DLD Inspection |  | 0 | 0
Code |  | 4 | 0.46107
Code Review |  | 0 | 0
Compile |  | 0 | 0
Code Inspection |  | 0.5 | 0
Unit Test |  | 0.2 | 0
Build and Integration Test |  | 0.02 | 0
System Test |  | 0 | 0.27586
Defect Removal Rates |  | Plan | Actual
Planning |  | 0 | 0
Requirements |  | 0 | 0
System Test Plan |  | 0 | 0
REQ Inspection |  | 0 | 0
High-Level Design |  | 0.1625 | 0
Integration Test Plan |  | 0 | 0
HLD Inspection |  | 0.47287 | 0
Detailed Design |  | 0 | 0
DLD Review |  | 0 | 0
Test Development |  | 1.5782 | 0
DLD Inspection |  | 0 | 0
Code |  | 2.0292 | 0.39747
Code Review |  | 0 | 0
Compile |  | 0 | 0
Code Inspection |  | 0 | 0
Unit Test |  | 1.4511 | 0.66667
Build and Integration Test |  | 0 | 0
System Test |  | 0.025797 | 0.27586

## SUMS
TSPi Size Summary - Form SUMS
| Name | Lohtu
| Team | B
| Date | 2026-07-29 19:52
| Instructor | Inkeri Verkamo
| Cycle | 3 |  |  |  | Planned Size | [7 empty] | Actual Size | [7 empty] | Planned Defects Injected | [17 empty] | Actual Defects Injected | [17 empty] | Planned Defects Removed | [17 empty] | Actual Defects Removed | [17 empty] | Planned Time | [21 empty] | Actual Time
Part ID | Part Name | Assembly/Part | Part of | Owner | Size Measure | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem
1 | Projektisuunnitelma | A | SYSTEM | AA | Text Pages | 11 | 0 | 2 | 0 | 0 | 2 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 11 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Määrittelydokumentti | A | SYSTEM | AA | Req Pages | 9 | 0 | 2 | 0 | 0 | 2 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Suunnitteludokumentti | A | SYSTEM | AA | HLD Pages | 37 | 0 | 5 | 0 | 0 | 5 | 37 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 37 | [19 empty] | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Testaussuunnitelma | A | SYSTEM | AA | Text Pages | 10 | 0 | 2 | 0 | 0 | 2 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | HTML-koodi | A | SYSTEM | AA | LOC | 365 | 50 | 50 | 700 | 0 | 750 | 1015 | 0 | 365 | 0 | 0 | 612 | 0 | 612 | 977 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Java-koodi | A | SYSTEM | AA | LOC | 2235 | 100 | 400 | 1000 | 200 | 1400 | 3335 | 0 | 2235 | 0 | 0 | 1661 | 0 | 1661 | 3896 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 2 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 3 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Tietokannanpäivitys/taulujen luonti | A | SYSTEM | AA | LOC | 135 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 135 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Loppuraportti | A | SYSTEM | AA | Text Pages | 7 | 0 | 0 | 10 | 0 | 10 | 17 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Task
TSPi Task Planning Template - Form TASK | [11 empty] | Total Plan Hours
Name | Lohtu | [10 empty] | 250
Team | B
Date | 2026-07-29 19:52
Instructor | Inkeri Verkamo
Cycle | 3 |  | Plan Hours by Role
Assembly | Phase | Task | Team Leader | Development Manager | Planning Manager | Quality/Process Manager | Support Manager | 0 | Total Resource Hours | Estimated Size | Size Measure | Rate (per Hr.) | Estimated Hours | Engrs | Plan Hours | Actual Hours | Actual Date | Actual Week | Earned Value | Cumulative EV | Cumulative Plan Hours | Plan Value |  | Plan Week | Plan Date
SYSTEM | MGMT | Projektisuunnitelman/aikataulujen päivitys | 1 | 0 | 0 | 1 | 0 |  | 2 | [5 empty] | 2 | 0.5 |  |  |  |  | 2 | 0.8 | 0.8 | 1 | 2003-04-01
SYSTEM | REQ | Määrittelyn päivitys | 1 | 0 | 0 | 1 | 0 |  | 2 | [5 empty] | 2 | 0.5 |  |  |  |  | 4 | 0.8 | 1.6 | 1 | 2003-04-01
SYSTEM | HLD | Suunnittelun päivitys | 0 | 5 | 0 | 0 | 0 |  | 5 | [5 empty] | 5 | [5 empty] | 9 | 2 | 3.6 | 1 | 2003-04-01
SYSTEM | HLDINSP | Suunnitteludokumentin katselmointi | 1 | 1 | 1 | 1 | 1 |  | 5 | [5 empty] | 5 | [5 empty] | 14 | 2 | 5.6 | 1 | 2003-04-01
SYSTEM | STP | Testaussuunnitelman päivitys | 0 | 0 | 0 | 1 | 0 |  | 1 | [5 empty] | 1 | 0.16667 |  |  |  |  | 15 | 0.4 | 6 | 1 | 2003-04-01
SYSTEM | HLD | Käyttötapausten päivitys | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | [5 empty] | 15 | 0 | 6 | 1 | 2003-04-01
SYSTEM | HLD | Käyttöliittymän suunnittelu | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | [5 empty] | 15 | 0 | 6 | 1 | 2003-04-01
SYSTEM | MGMT | Viikkopalaverit | 10 | 7 | 7 | 10 | 7 |  | 41 | [5 empty] | 41 | 12.7667 |  |  |  |  | 56 | 16.4 | 22.4 | 2 | 2003-04-08
SYSTEM | CODE | Java-koodaus | 8 | 10 | 10 | 5 | 10 |  | 43 | [5 empty] | 43 | 54.1178 |  |  |  |  | 99 | 17.2 | 39.6 | 2 | 2003-04-08
SYSTEM | CODE | Html/jsp-koodaus | 2 | 2 | 4 | 5 | 2 |  | 15 | [5 empty] | 15 | 0.75 |  |  |  |  | 114 | 6 | 45.6 | 3 | 2003-04-15
SYSTEM | CR | Koodin katselmointi | 5 | 5 | 5 | 5 | 5 |  | 25 | [5 empty] | 25 | [5 empty] | 139 | 10 | 55.6 | 4 | 2003-04-22
SYSTEM | ST | Järjestelmätestaus | 5 | 5 | 5 | 5 | 5 |  | 25 | [5 empty] | 25 | 7.25 |  |  |  |  | 164 | 10 | 65.6 | 5 | 2003-04-29
SYSTEM | UT | Yksikkötestaus | 5 | 5 | 5 | 5 | 5 |  | 25 | [5 empty] | 25 | 6 |  |  |  |  | 189 | 10 | 75.6 | 5 | 2003-04-29
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2 | 2 | 5 | 2 | 2 |  | 13 | [5 empty] | 13 | 20.9847 |  |  |  |  | 202 | 5.2 | 80.8 | 6 | 2003-05-06
SYSTEM | MGMT | Yleinen projektin hallinta | 2 | 1 | 1 | 1 | 1 |  | 6 | [5 empty] | 6 | 18.0819 |  |  |  |  | 208 | 2.4 | 83.2 | 6 | 2003-05-06
SYSTEM | PM | Postmortem | 3 | 3 | 3 | 3 | 3 |  | 15 | [5 empty] | 15 | 3 |  |  |  |  | 223 | 6 | 89.2 | 6 | 2003-05-06
SYSTEM | TD | Sovellusympäristön hallinnointi | 0 | 0 | 0 | 0 | 5 |  | 5 | [5 empty] | 5 | 10.05 |  |  |  |  | 228 | 2 | 91.2 | 6 | 2003-05-06
SYSTEM | AT | Käyttöohjeiden tekeminen | 1 | 0 | 0 | 1 | 0 |  | 2 | [5 empty] | 2 | 4.8114 |  |  |  |  | 230 | 0.8 | 92 | 6 | 2003-05-06
SYSTEM | AT | Käyttöohjeiden katselmointi | 2 | 2 | 2 | 2 | 2 |  | 10 | [5 empty] | 10 | 1 |  |  |  |  | 240 | 4 | 96 | 6 | 2003-05-06
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2 | 2 | 2 | 2 | 2 |  | 10 | [5 empty] | 10 | 12.5 |  |  |  |  | 250 | 4 | 100 | 6 | 2003-05-06
0
Update Task and Schedule Plan
Generate Task List

## Schedule
TSPi Schedule Planning Template - Form SCHEDULE
| Name | Lohtu
| Team | B |  |  |  |  | Total Task Plan Hours | 250
| Date | 2026-07-29 19:52 |  |  |  |  | Total Schedule Plan Hours | 250
| Instructor | Inkeri Verkamo |  |  |  |  | Difference | 0
| Cycle | 3
Date | Week | Planned Hours | Cumulative Planned Hours | Actual Hours | Cumulative Actual Hours | Planned Value | Cumulative Planned Value | Earned Value | Cumulative EV | Predicted Hours | Cumulative Predicted Hours | Predicted Earned Value | Cumulative Predicted Earned Value
2003-04-01 | 1 | 50 | 50 | 29.5333 | 29.5333 | 6 | 6 | 0 | 0
2003-04-08 | 2 | 50 | 100 | 18.4525 | 47.9858 | 33.6 | 39.6 | 0 | 0
2003-04-15 | 3 | 20 | 120 | 0 | 47.9858 | 6 | 45.6 | 0 | 0
2003-04-22 | 4 | 30 | 150 | 20.6167 | 68.6025 | 10 | 55.6 | 0 | 0
2003-04-29 | 5 | 50 | 200 | 24.3214 | 92.9239 | 20 | 75.6 | 0 | 0
2003-05-06 | 6 | 50 | 250 | 50.2864 | 143.2103 | 24.4 | 100 | 0 | 0
2003-05-13 | 7 |  |  | 9.2689 | 152.4792 |  |  | 0 | 0

## Risk (hidden)
Risk | Impact | Likelihood | Priority | Assigned | Date

## LOGT
TSPi Time Recording Log - Form LOGT
Name | Lohtu |  |  | Date | 2026-07-29 19:52
Team | B |  |  | Instructor | Inkeri Verkamo
|  |  |  | Cycle | 3
Assembly | Phase | Task | Date | Start | Int. | Stop | Delta | Comments
SYSTEM | MGMT | Viikkopalaverit | 2003-04-01 | 9:00 |  | 10:00 | 60 | Viikkopalaveri
SYSTEM | TD | Sovellusympäristön hallinnointi | 2003-04-01 | 13:00 |  | 15:40 | 160 | Tomcat säätö
SYSTEM | TD | Sovellusympäristön hallinnointi | 2003-04-03 | 14:30 |  | 16:30 | 120 | Tomcat säätö
SYSTEM | MGMT | Viikkopalaverit | 2003-04-07 | 8:05 |  | 8:35 | 30 | Viikkopalaveri
SYSTEM | TD | Sovellusympäristön hallinnointi | 2003-04-07 | 8:45 |  | 11:30 | 165 | Tomcat säätö
SYSTEM | CODE | Yksikkötestaus | 2003-04-07 | 12:00 |  | 15:30 | 210 | Junit testien teko
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-04-07 | 16:30 |  | 17:00 | 30 | Dokkarien kääntö pdf:ksi ja päivitys verkkoon sekä tuntien kirjaus
SYSTEM | TD | Sovellusympäristön hallinnointi | 2003-04-10 | 14:30 |  | 15:00 | 30 | Tomcat säätö
SYSTEM | TD | Sovellusympäristön hallinnointi | 2003-04-12 | 21:00 |  | 23:08 | 128 | Tomcat säätö
SYSTEM | MGMT | Viikkopalaverit | 2003-04-14 | 8:40 |  | 9:00 | 20 | Viikkopalaveri
SYSTEM | CODE | Java-koodaus | 2003-04-14 | 9:10 |  | 12:18 | 188 | Syklin suunnittelun koodausta
SYSTEM | CODE | Java-koodaus | 2003-04-14 | 12:57 |  | 14:47 | 110 | Syklin suunnittelun koodausta
SYSTEM | CODE | Java-koodaus | 2003-04-25 | 9:40 |  | 12:30 | 170 | Syklin suunnittelun koodausta
SYSTEM | CODE | Java-koodaus | 2003-04-25 | 13:00 |  | 15:25 | 145 | Syklin suunnittelun koodausta
SYSTEM | CODE | Java-koodaus | 2003-04-28 | 9:00 |  | 12:14 | 194 | Syklin suunnittelun koodausta
SYSTEM | CODE | Java-koodaus | 2003-04-28 | 12:40 |  | 16:38 | 238 | Syklin suunnittelun koodausta
SYSTEM | CODE | Java-koodaus | 2003-05-02 | 11:50 |  | 15:50 | 240 | Syklin suunnittelun koodausta
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-05-03 | 22:05 |  | 22:32 | 27 | websivujen päivitys
SYSTEM | CODE | Java-koodaus | 2003-05-04 | 21:19 |  | 23:59 | 160 | Syklin suunnittelun koodausta
SYSTEM | MGMT | Viikkopalaverit | 2003-05-05 | 8:05 |  | 8:55 | 50 | Viikkopalaveri
SYSTEM | CODE | Java-koodaus | 2003-05-05 | 9:04 |  | 11:02 | 118 | Syklin suunnittelun koodausta
SYSTEM | CODE | Java-koodaus | 2003-05-05 | 11:28 |  | 15:30 | 242 | Syklin suunnittelun koodausta
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-05-06 | 16:10 |  | 16:40 | 30 | Javadocien teko
SYSTEM | CODE | Java-koodaus | 2003-05-07 | 9:40 |  | 11:36 | 116 | Syklin suunnittelun koodausta
SYSTEM | CODE | Java-koodaus | 2003-05-07 | 13:32 |  | 15:21 | 109 | Syklin suunnittelun koodausta
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-07 | 22:01 |  | 22:10 | 8.9333 | Tuntien täyttö
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-05-07 | 22:10 |  | 22:25 | 14.9167 | Dokkarien kääntö pdf:ksi ja päivitys verkkoon
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-07 | 22:26 |  | 22:34 | 8.5 | Virheiden kirjaus
SYSTEM | CODE | Java-koodaus | 2003-04-01 | 12:00 |  | 13:28 | 88 | Koodausta
SYSTEM | CODE | Java-koodaus | 2003-04-01 | 14:00 |  | 14:16 | 16 | Koodausta
SYSTEM | CODE | Java-koodaus | 2003-04-01 | 15:00 |  | 15:20 | 20 | Koodausta (onko enää edes ihme)
SYSTEM | CODE | Java-koodaus | 2003-04-02 | 11:15 |  | 12:01 | 46 | Koodausta (taas)
SYSTEM | CODE | Java-koodaus | 2003-04-07 | 8:50 |  | 11:59 | 189 | Koodausta
SYSTEM | CODE | Java-koodaus | 2003-04-10 | 14:32 |  | 17:06 | 154.4667 | koodausta taas kerran.
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-08-03 | 11:35 |  | 14:59 | 204 | loppuraportin perusasioiden kirjoittelua
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-08-06 | 19:30 |  | 20:02 | 32 | Loppuraportin kirjoittelua
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-05-08 | 13:30 |  | 14:47 | 77 | Loppuraportin säätämistä
SYSTEM | MGMT | Viikkopalaverit | 2003-05-08 | 8:00 |  | 13:00 | 300 | Tässä ovat syklin tähänastiset viikkopalaverit tuntimääräisesti
SYSTEM | AT | Käyttöohjeiden tekeminen | 2003-04-14 | 8:00 |  | 8:30 | 30 | käyttöohjeen rungon tekeminen
SYSTEM | MGMT | Viikkopalaverit | 2003-04-14 | 8:30 |  | 9:00 | 30 | 3.syklin 3.vkopalaveri
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-04-14 | 9:00 |  | 9:15 | 15 | TSP-työkaluihin tehtävien lisäyksiä
SYSTEM | CODE | Java-koodaus | 2003-04-14 | 9:15 |  | 9:45 | 30 | checkstyle virheiden korjausta
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-04-14 | 14:38 |  | 14:48 | 10.0833 | TSP-työkaluun virheiden lisäykset
SYSTEM | CODE | Java-koodaus | 2003-04-14 | 14:48 |  | 16:07 | 79.1833 | PhaseVO
SYSTEM | CODE | Java-koodaus | 2003-04-14 | 17:13 |  | 17:30 | 17.4167
SYSTEM | AT | Käyttöohjeiden tekeminen | 2003-04-24 | 14:00 |  | 14:30 | 30
SYSTEM | AT | Käyttöohjeiden tekeminen | 2003-04-27 | 18:00 |  | 19:00 | 60
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-04-27 | 19:00 |  | 19:30 | 30
SYSTEM | PM | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-04-29 | 19:00 |  | 21:15 | 134.75 | TSP-yhteeveto
SYSTEM | AT | Käyttöohjeiden tekeminen | 2003-04-29 | 21:10 |  | 21:48 | 37.5 | Sovelluksen käyttöohjeen kirjoittaminen
SYSTEM | MGMT | Viikkopalaverit | 2003-04-28 | 8:15 |  | 9:00 | 45 | 3.syklin 4.vkopalaveri
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-04-28 | 9:00 |  | 9:30 | 30 | keskustelua projektista
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-04-28 | 9:30 |  | 10:45 | 75 | TSP-lomakkeiden läpikäyminen
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-03 | 12:01 |  | 13:22 | 81.8167 | TSP-yhteenvedon tekeminen
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-03 | 13:50 |  | 15:40 | 109.7833 | "
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-03 | 16:07 |  | 17:51 | 103.4333 | "
SYSTEM | MGMT | Viikkopalaverit | 2003-05-05 | 8:15 |  | 9:00 | 45 | 3.syklin 5.vkopalaveri
SYSTEM | AT | Käyttöohjeiden tekeminen | 2003-05-06 | 19:04 |  | 20:30 | 85.7667 | käyttöohjeen kirjoitus
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-08 | 17:00 |  | 19:14 | 134.1667 | tsp-yhteenveto
SYSTEM | AT | Käyttöohjeiden tekeminen | 2003-05-08 | 19:15 |  | 20:00 | 45.4167 | käyttöohje valmiiksi
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-08 | 21:25 |  | 22:49 | 84.1 | ja tsp-yhteenvetoa
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-09 | 8:17 |  | 12:30 | 253.3833 | "
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-11 | 19:15 |  | 21:15 | 120
SYSTEM | PM | Postmortem | 2003-05-11 | 21:15 |  | 22:00 | 45 | valmistautuminen
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-05-12 | 13:00 |  | 14:00 | 60
SYSTEM | PM | Postmortem | 2003-05-12 | 14:00 |  | 15:00 | 60
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-12 | 15:00 |  | 16:00 | 60
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-15 | 16:00 |  | 18:00 | 120
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-15 | 18:55 |  | 20:55 | 120.1333
SYSTEM | MGMT | Viikkopalaverit | 2003-04-01 | 9:00 |  | 9:45 | 45
SYSTEM | CODE | Java-koodaus | 2003-04-06 | 19:00 |  | 20:30 | 90 | Ekan syklin toteutus
SYSTEM | MGMT | Viikkopalaverit | 2003-04-07 | 8:07 |  | 8:33 | 26
SYSTEM | CODE | Java-koodaus | 2003-04-07 | 8:33 | 90 | 17:00 | 417
SYSTEM | CODE | Java-koodaus | 2003-04-13 | 19:30 |  | 20:40 | 70 | Ekan syklin toteutus/ yleinen härväys ja tuntien kirjaus
SYSTEM | MGMT | Viikkopalaverit | 2003-04-14 | 8:30 |  | 9:00 | 30 | Projektikokous ja yleinen keskustelu
SYSTEM | ST | Järjestelmätestaus | 2003-04-14 | 9:00 |  | 11:30 | 150 | Ekan syklin loppuun saattaminen
SYSTEM | ST | Yleinen projektin hallinta | 2003-04-27 | 20:00 |  | 20:30 | 30 | Yleistä projektin tilanteen tarkastelua
SYSTEM | ST | Yksikkötestaus | 2003-04-27 | 20:30 |  | 23:00 | 150 | Yksikkl testaus
SYSTEM | ST | Yleinen projektin hallinta | 2003-05-12 | 8:00 |  | 11:00 | 180 | Loppuraportti + mailit ja uudet dokumentit
SYSTEM | ST | Yleinen projektin hallinta | 2003-05-12 | 13:00 | 60 | 18:30 | 270 | Loppudemo + kokous + yleistä projektin lopettelua
SYSTEM | MGMT | Projektisuunnitelman/aikataulujen päivitys | 2003-04-07 | 15:45 |  | 16:15 | 30 | Projektisuunnitelman ja Gannt-kaavion päivitys
SYSTEM | REQ | Määrittelyn päivitys | 2003-04-07 | 16:15 |  | 16:45 | 30 | Määrittelydokumentin päivitys
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-04-11 | 20:55 |  | 21:10 | 15 | TSP-työkalun päivitys
SYSTEM | MGMT | Viikkopalaverit | 2003-04-28 | 8:05 |  | 8:45 | 40 | viikkopalaveri
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-04-29 | 21:20 |  | 21:50 | 30 | 2. syklin 2. katselmoinnin virheiden syöttö työkaluun
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-04-29 | 21:50 |  | 22:05 | 15 | viikkopalaverin pöytäkirjan kirjoitus
SYSTEM | STP | Testaussuunnitelman päivitys | 2003-04-29 | 22:30 |  | 22:40 | 10 | testaussuunnitelman päivitys
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-04-29 | 22:40 |  | 22:50 | 10 | tuntien syöttö
SYSTEM | MGMT | Viikkopalaverit | 2003-05-05 | 8:10 |  | 8:55 | 45 | viikkopalaveri
SYSTEM | ST | Järjestelmätestaus | 2003-05-06 | 10:20 |  | 10:50 | 30 | Taistelua testauksen kanssa…
SYSTEM | ST | Järjestelmätestaus | 2003-05-06 | 11:04 |  | 12:04 | 60 | testausta
SYSTEM | CODE | Html/jsp-koodaus | 2003-05-06 | 12:05 |  | 12:25 | 20 | css-viilausta
SYSTEM | ST | Järjestelmätestaus | 2003-05-06 | 13:00 |  | 14:45 | 105 | testiraportti + testaussuunnitelman päivitys
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-05-06 | 14:45 |  | 15:00 | 15 | viikkopalaverin pöytäkirjan kirjoitus
SYSTEM | AT | Käyttöohjeiden katselmointi | 2003-05-07 | 10:55 |  | 11:55 | 60 | käyttöohjeen luku ja kommentointi, testauksesta spostittelua
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-07 | 11:50 | 45 | 14:00 | 85 | demotilaisuuden powerpointin tekoa
SYSTEM | CODE | Html/jsp-koodaus | 2003-05-08 | 10:20 |  | 10:30 | 10 | css-viilausta
SYSTEM | CODE | Html/jsp-koodaus | 2003-05-08 | 10:35 |  | 10:50 | 15 | CyclePlanningin poistovarmistusten päivitys
SYSTEM | ST | Järjestelmätestaus | 2003-05-08 | 10:50 |  | 11:40 | 50 | testaus
SYSTEM | ST | Järjestelmätestaus | 2003-05-08 | 13:30 |  | 14:10 | 40 | testiraportin kirjoitus
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-08 | 14:15 |  | 15:30 | 75 | TSP-laatuyhteenvedon kirjoitus
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-08 | 15:30 |  | 15:55 | 25 | tuntien syöttö ja virheiden kirjaus
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-12 | 9:00 |  | 11:15 | 135 | TSP-laatuyhteenvedon kirjoitus
SYSTEM | PM | Postmortem | 2003-05-12 | 11:15 |  | 11:45 | 30 | vertaisarviointi + projektin pohdintaa postmortemia varten
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-12 | 13:00 |  | 14:00 | 5 | Demoon valmistautumista
SYSTEM | PM | Postmortem | 2003-05-12 | 14:00 |  | 14:45 | 45 | Postomortem
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-12 | 15:00 |  | 16:00 | 60 | Demoon valmistautumista
SYSTEM | AT | Demotilaisuus+siihen valmistautuminen | 2003-05-12 | 16:15 |  | 17:45 | 90 | Demotilaisuus
SYSTEM | MGMT | Yleinen projektin hallinta | 2003-05-14 | 10:40 |  | 12:00 | 70 | Laatukommentit TSp-yhteenvetoon
SYSTEM | MGMT | TSP-työkalu, päivitys/tuntien ja vikatietojen kirjaus | 2003-05-14 | 12:00 |  | 12:50 | 10 | tuntien syöttö

## LOGD
TSPi Defect Recording Log - Form LOGD
Name | Lohtu |  |  | Date | 2026-07-29 19:52
Team | B |  |  | Instructor | Inkeri Verkamo
|  |  |  | Cycle | 3
Date | Num | Type | Assembly | Injected | Removed | Fix Time | Fix Ref. | Description
2003-04-07 | 1 | 40 | Java-koodi | CODE | UT | 1 |  | metodin parametriä ei asetettu TaskVO:n setMilestone metodissa
2003-04-14 | 2 | 20 | Java-koodi | CODE | UT | 3 |  | CyclePlanning
2003-04-14 | 3 | 20 | Java-koodi | CODE | UT | 2 |  | CyclePlanning
2003-04-14 | 4 | 20 | Java-koodi | CODE | CODE | 5 |  | CyclePlanning
2003-04-14 | 5 | 20 | Java-koodi | CODE | UT | 1 |  | CyclePlanning
2003-04-14 | 6 | 20 | Java-koodi | CODE | CODE | 5 |  | CyclePlanning
2003-04-14 | 7 | 20 | Java-koodi | CODE | CODE | 8 |  | TaskDAO
2003-04-14 | 8 | 20 | Java-koodi | CODE | CODE | 3 |  | UserDAO
2003-04-14 | 9 | 20 | Java-koodi | CODE | CODE | 1 |  | TASKVO
2003-03-28 | 10 | 80 | Suunnitteludokumentti | HLD | CODE | 30 |  | ei setDelete ja isDeleted metodeja UsersTaskVO:ssa
2003-03-28 | 11 | 40 | Suunnitteludokumentti | HLD | CODE | 10 |  | PhaseVOssa ei asetettu pakollista namea konstruktorissa
2003-03-28 | 12 | 60 | Java-koodi | CODE | CODE | 25 |  | PhaseDAO, ei otettu huomioon mahdollisuutta nulleihin
2003-03-28 | 13 | 60 | Java-koodi | CODE | CODE | 5 |  | TaskDAO, ei otettu huomioon mahdollisuutta nulleihin
2003-03-28 | 14 | 20 | Java-koodi | CODE | CODE | 4 |  | PhaseDAO, yksi tietokantakenttä liikaa SQL-lauseessa
2003-03-28 | 15 | 20 | Java-koodi | CODE | CODE | 8 |  | PhaseDAO, SQL-lause päin honkia
2003-03-28 | 16 | 40 | Java-koodi | CODE | COMPILE | 24 |  | TaskVO, ylimääräinen konstruktori
2003-03-28 | 17 | 40 | Java-koodi | CODE | COMPILE | 1 |  | TaskVO, konstruktorin syktaksi väärin
2003-03-28 | 18 | 50 | Java-koodi | CODE | COMPILE | 5 |  | TaskVO, konstruktorissa ei asetettu componentId:tä
2003-05-07 | 19 | 40 | Java-koodi | CODE | CODE | 1 |  | TaskDAO:n getTaskIterator metodissa ei asetettu tehtävän deadlinea.
2003-05-07 | 20 | 40 | Java-koodi | CODE | CODE | 3 |  | UserTaskDAO:ssa iteraattoria muodostettaessa UserTaskVO:n konstruktorin parametrit väärinpäin.
2003-05-07 | 21 | 40 | Java-koodi | CODE | CODE | 5 |  | ComponentDAO:ssa iteraattoria muodostettaessa SQL-lauseesta oli unohtunut asettaa parametri.
2003-05-07 | 22 | 50 | Suunnitteludokumentti | HLD | CODE | 2 |  | ProjectDAO:n saveProject -metodin tulee palauttaa void eikä int
2003-05-07 | 23 | 60 | Java-koodi | CODE | CODE | 2 |  | CycleControllerissa jos ei ollut vaiheen alkamisaikaa, sitä verrattiin loppumisaikaan, jolloin tuli nullpointerexception
2003-05-07 | 24 | 60 | Java-koodi | CODE | CODE | 35 |  | CyclePlanning.jsp:stä oli unohtunut tapaus, jossa ohjelmiston osia ei ole olemassa.
2003-05-07 | 25 | 60 | Java-koodi | CODE | CODE | 85 |  | TaskDAO:n tallennus metodissa ei oltu ajateltu tyhjän componentId:n eikä tyhjien päivämäärien tarkistusta
2003-04-07 | 26 | 60 | HTML-koodi | CODE | CODE | 10 |  | Virhe ProjectBasics JSP sivulla
2003-04-07 | 27 | 60 | HTML-koodi | CODE | CODE | 10 |  | Virhe ProjectBasics JSP sivulla
2003-04-07 | 28 | 60 | Java-koodi | CODE | CODE | 10 |  | ProjectControler
2003-04-07 | 29 | 60 | Java-koodi | CODE | CODE | 10 |  | ProjectDAO
2003-04-07 | 30 | 60 | Java-koodi | CODE | CODE | 10 |  | SoftwareTypeDAO
2003-04-07 | 31 | 60 | Java-koodi | CODE | CODE | 10 |  | ProjectBasics JSP sivulla
2003-04-07 | 32 | 60 | Java-koodi | CODE | CODE | 5 |  | ComponentDAO
2003-04-14 | 33 | 60 | Java-koodi | ST | ST | 10 |  | ProjectControler
2003-04-14 | 34 | 60 | Java-koodi | ST | ST | 5 |  | Virhe ProjectBasics JSP sivulla
2003-04-07 | 35 | 50 | SYSTEM | CODE | CODE | 1 |  | LohtuResources-luokassa on funktio formatDate eikä getDate.
2003-04-07 | 36 | 50 | SYSTEM | CODE | CODE | 1 |  | LohtuResources-luokassa on funktio formatDate eikä getDate.
2003-04-07 | 37 | 50 | SYSTEM | CODE | CODE | 1 |  | LohtuResources-luokassa on funktio formatDate eikä getDate.
2003-05-08 | 38 | 20 | SYSTEM | CODE | ST | 15 |  | CyclePlanningin poistovarmistusten siirto nappulan yhteyteen ja myös vaiheen poistoon.

## Week
TSPi Week Summary - Form WEEK
Name | Lohtu |  | Date | 2026-07-29 19:52
Team | B |  | Instructor | Inkeri Verkamo
Week | 1 |  | Cycle | 3
Weekly Data |  |  | Plan | Actual
Project hours for this week |  |  | 50 | 41.3781
Project hours this cycle to date |  |  | 50 | 41.3781
Earned value for this week |  |  | 6 | 0
Earned value this cycle to date |  |  | 6 | 0
Total hours for the tasks completed this phase to date
Team Member Weekly Data | Team Plan Hours | Team Actual Hours | Team Plan Value | Team Earned Value
Team Leader
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
0
Totals | 0 | 0 | 0 | 0
Development Tasks Completed | Plan Hours | Actual Hours | Earned Value | Plan Week

## DefectTypes
Type | Description
10 | Documentation
20 | Syntax
30 | Build, Package
40 | Assignment
50 | Interface
60 | Checking
70 | Data
80 | Function
90 | System
100 | Environment

## Phases (hidden)
Phase | Description | Task Generator S-System P-Part N-None | LOGT Track Time | LOGD Track Defects Injected | LOGD Track Defects Removed | PDF | DefDen | DefRatios | DevTimeRatio | RvwRate | PhaseYld | ProcYld | DI Rate | DR Rate
MGMT | Management and Miscellaneous | S | Y | N | N | N | N |  |  | N | N | N | N | N
STRAT | Launch and Strategy | S | Y | N | N | N | N |  |  | N | N | N | N | N
PLAN | Planning | S | Y | Y | Y | N | N |  |  | N | Y | Y | Y | Y
REQ | Requirements | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
STP | System Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
REQINSP | REQ Inspection | S | Y | Y | Y | N | Y |  | Requirements | Y | Y | N | Y | Y
HLD | High-Level Design | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
ITP | Integration Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
HLDINSP | HLD Inspection | S | Y | Y | Y | N | Y |  | High-Level Design | Y | Y | N | Y | Y
DLD | Detailed Design | P | Y | Y | Y | N | N |  | Code | N | Y | N | Y | Y
DLDR | DLD Review | P | Y | Y | Y | N | Y | Unit Test | Detailed Design | Y | Y | N | Y | Y
TD | Test Development | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
DLDINSP | DLD Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
CODE | Code | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
CR | Code Review | P | Y | Y | Y | N | Y | Compile | Code | Y | Y | N | Y | Y
COMPILE | Compile | P | Y | Y | Y | y | Y |  |  | N | Y | Y | Y | Y
CODEINSP | Code Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
UT | Unit Test | P | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
IT | Build and Integration Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
ST | System Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
DOC | Documentation | S | Y | N | N | N | N |  |  | N | N | N | N | N
PM | Postmortem | S | Y | N | N | N | N |  |  | N | N | N | N | N
AT | Acceptance Test | N | N | N | Y | Y | Y |  |  | N | N | Y | N | N
PL | Product Life | N | N | N | Y | Y | Y |  |  | N | N | N | N | N
Copyright 1998 James W. Over

## QProfParam
Parameter | Value | Description
Design/Code Time | 50% | Design time as % of coding time
Code Review Time | 50% | Code review time as % of code time
Compile Defects/KLOC | 10 | Compile defects/KLOC
Unit Test Ddefects/KLOC | 5 | Unit test defects/KLOC
Design Review Time | 50% | Design review time as % of design time
Restore Qprofile Parameter Defaults